## Sheet1
FARMSTEAD |  |  |  | DEADLINE 20/08/2023 |  |  |  |  | 2023-08-11 | 45149.4623
Tasks Name | Start Build | Deadline | Total (h) | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
HEADER | 2023-07-08 | 2023-07-08 | 2h | 0% | Nguyễn Thành Đạt | 2023-11-08 |  | 95% | Nguyễn Quang Mẫn
BANNER | 2023-08-08 | 2023-08-08 | 5h |  | Nguyễn Thành Đạt | 2023-11-08 |  | 100% | Nguyễn Quang Mẫn
FEATURES | 2023-09-08 | 2023-09-08 | 5h |  | Nguyễn Thành Đạt | 2023-12-08 |  |  | Nguyễn Quang Mẫn
SERVICES | 2023-10-08 | 2023-10-08 |  |  | Nguyễn Thành Đạt | 2023-12-08 |  |  | Nguyễn Quang Mẫn
REASONS | 2023-07-08 | 2023-07-08 | 2h | 100% | Nguyễn Quang Mẫn | 2023-11-08 |  |  | Nguyễn Thành Đạt
REASONS | 2023-08-08 | 2023-08-08 | 3h | 100% | Nguyễn Quang Mẫn | 2023-11-08 |  |  | Nguyễn Thành Đạt
GALLERY | 2023-08-08 | 2023-08-08 |  | 100% | Nguyễn Quang Mẫn | 2023-11-08 |  |  | Nguyễn Thành Đạt
FEEDBACK | 2023-10-08 | 2023-10-08 | 2h | 100% | Nguyễn Quang Mẫn | 2023-12-08 |  |  | Nguyễn Thành Đạt
FOOTER | 2023-11-08 | 2023-11-08 | 1h | 80% | Nguyễn Quang Mẫn | 2023-12-08 |  |  | Nguyễn Thành Đạt
BACKTOTOP | 2023-12-08 | 2023-12-08 |  |  | Nguyễn Quang Mẫn | 2023-12-08 |  |  | Nguyễn Thành Đạt